## Project Timeline
Crab Shack Kitchen |  | Please fill in the date when you start and complete the event (MM/DD)
Events |  | Start | Complete
Group and App Selection Phase
| Group selection | 2016-01-12 | 2016-01-14
| App selection | 2016-01-12 | 2016-01-19
| Group name & leaders | 2016-01-14 | 2016-01-14
Design phase
| Overview of project | 2016-01-25 | 2016-01-28
| Stakeholder description | 2016-01-25 | 2016-01-25
| Personas | 2016-01-25 | 2016-01-25
| Evironment description | 2016-01-25 | 2016-01-28
| Nominal interaction diagram | 2016-01-25
| Nominal scenarios | 2016-01-25 | 2016-01-25
| Hierachical task analysis | 2016-01-25 | 2016-01-25
| Database schema | 2016-01-25 | 2016-01-28
Paper prototype and Walkthrough phase
Paper prototype
User scenarios
Usability goals and concerns list
Cognitive walkthrough
Design changes phase
Design changes document
Implementation phase
Tested App with phones
Package name
Database schema update
Functionalities
Help documentation implemented
Final Review phase
Final review with scientist
Changes after review (optional)
Usability testing phase
Scheduled (hour & room)
Conducted tests
Closure phase
Website complete
Documentation complete