## Sheet1
| Project: | Team 3 - Green StormWater 🟩⛈️
Burndown Table
Timeline
|  | Estimated Effort | Week
Catagory | Product Backlog Inventory (PBI) | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Enter task estimated effort in this column
init | Init with Grails | bar: Estimated Effort 0 to Week 15
| Navbar | Estimated Effort 0: 3; Week 8: 3
Static info | Home Page | Estimated Effort 0: 3; Week 9: 3
| Info page | Estimated Effort 0: 3; Week 10: 3
Contact page | bar: Estimated Effort 0 to Week 15
Static map | Create Map Page | Estimated Effort 0: 2; Week 11: 2
| Link Map API on Map page | Estimated Effort 0: 5; Week 12: 4
Observations | Create Input form page | bar: Estimated Effort 0
| Create database | Estimated Effort 0: 5; Week 11: 4
| Create post form | Estimated Effort 0: 3; Week 12: 2
List view page | bar: Estimated Effort 0 to Week 15
| List view functions | Estimated Effort 0: 5; Week 10: 2
Spring Security | Implement spring | Estimated Effort 0: 2; Week 13: 4
| Login page | Estimated Effort 0: 3; Week 13: 2
| functions of app | Estimated Effort 0: 5; Week 14: 2
Manage accounts | CRUD accounts page | Estimated Effort 0: 8
| Remaing Effort | 51 | 51 | 51 | 51 | 51 | 51 | 51 | 50 | 47 | 44 | 38 | 32 | 25 | 19 | 17 | 17
| Ideal | 47 | 43.8667 | 40.7333 | 37.6 | 34.4667 | 31.3333 | 28.2 | 25.0667 | 21.9333 | 18.8 | 15.6667 | 12.5333 | 9.4 | 6.2667 | 3.1333 | 0
| Target: | Estimated Effort 0: 0